Scheme Name	Mays Lane and surrounding area road safety measures
Date of correspondence	23 May 2025
Our ref	Mays Lane
Location	Mays Lane and surrounding area
Start Date	13 March 2025
Duration of works	Approximately 7-8 months
Contact Details	t. 0208 359 3555 / e. highwayscorrespondence@barnet.gov.uk

Dear Resident / Business

Re: Mays Lane and surrounding area road safety measures

We are writing to update you on the safety improvement works being undertaken on Mays Lane and surrounding roads.

Firstly, please accept our apology for the impact and disruption the introduction of these road safety measures is having on you and the local area.

We wrote to residents on the 4 February 2025 to provide confirmation of the upcoming works which include a number of engineering measures. These measures were identified following a feasibility study of the area. The list of agreed measures can be found by searching Mays Lane on engage.barnet.gov.uk/closed-projects.

Following a number of enquiries regarding the ongoing works, we would like to reassure residents that we are reviewing your concerns which mainly relate to:

The removal of the width restriction and temporary road service
Chesterfield Road kerb alignment and double yellow lines
Chesterfield Road parking
The junction of Underhill and the High Road
Speed cushions and raised tables around Whitings Road Primary School
Traffic congestion and flow through the area
Duration and programme of works.

The removal of the width restriction and temporary road service

The width restriction removal is a result of requests from the Emergency Services and local residents.

To mitigate the removal of the width restriction, we have introduced a new zebra crossing which sits on a raised table

These works are being completed in phases:
1. Phase 1 – the width restriction removal, raised table installation and temporary markings
2. Phase 2 – permanent resurfacing and line markings
3. Phase 3 – lighting installation for the zebra

To guarantee safety please note that the crossing will remain barriered off until all the above elements are completed.

Chesterfield Road kerb alignment and double yellow lines

A site visit was undertaken at this location and we:

  1. monitored the impact that the temporary signals at the Bells Hill junction had on Chesterfield Road through morning and afternoon site inspections. These temporary signals have now been removed.
  2. are reviewing options for the bus stop.
  3. engaged with TfL to seek their views on bus stop usage.
  4. are in ongoing discussions with TfL in relation to the buses using the stop at the junction as a bus stand.
  5. are reviewing options for the introduction of the CPZ extension in the area.

Chesterfield Road parking

As above, we are reviewing options for the introduction of the CPZ extension in the area.

Junction of Underhill and the High Road

We will be reviewing this junction as a separate scheme and have arranged a meeting onsite between the Highways Manager and a resident representative to discuss concerns.

Speed cushions and raised tables around Whitings Road Primary School

The speed cushions and raised table on Quinta Drive and Whitings Road have been introduced in accordance with our detailed design, following a Road Safety Audit and statutory consultation.

Traffic congestion and flow through the area

There are three schemes currently being undertaken in the area:

1. Mays Lane and surrounding area road safety measures
2. Ark Pioneer Academy safety measures
3. Ark Pioneer Academy - review of existing single yellow lines consultation

So that we can complete works for point “1” and “2” above safely, temporary traffic management, including the use of temporary signals, is required.

All Ark Pioneer Academy safety measures are due to be installed by Friday 23 May 2025, with all traffic management associated with this scheme to be removed following completion.

Duration of works

Due to the scale and nature of the introduction of road safety measures on Mays Lane and surrounding area, it is anticipated that these works will be completed by the end of August.

We appreciate that these works have created additional traffic throughout the area and that phased elements may have caused confusion around whether works were completed.

Furthermore, we understand that not everyone will be entirely happy with the measures being introduced and ask for your patience during this period whilst the work is completed.

I confirm following completion of all works, we will monitor the effectiveness of the measures introduced and complete a Road Safety Audit stage 3 (RSA3). If required, we may make further changes, although this is not guaranteed and is dependent on the outcome of the RSA3.

If changes are identified following the RSA3, we will write to you to provide further details.

For further information on our Mays Lane and surrounding area road safety measures scheme, and for latest updates, scan the QR code opposite, or visit: barnet.gov.uk/roads-and-pavements/major-highways-projects.

We would like to thank you for your patience during the installation of the road safety measures on Mays Lane and surrounding area.

If you have any further questions on this scheme, please get in touch using the contact details above.

Yours faithfully,

Daniela Pometti
Head of Highways Asset Management